## Cost to Complete
Cost to Complete
Through 05/19/2026
Original Budget | $131,000
Current Budget | $136,206 | ▲ $5.2k vs. original
Projected Cost at Completion | $130,131
Projected Gross Profit | $15,200 | ▲ $869.16 vs. original ▲ 10.5% GP margin
Current Contract Value | $145,330 | Through May 19, 2026
COST CODE | CATEGORY | ORIGINAL BUDGET | COR | CURRENT BUDGET | COMMITTED | REMAINING | % USED | ADJUSTMENT | AT COMPLETION
Labor |  | 87500 | 4600 | 92100 | 84100 | 8000 | 91 | -9060 | 88470
CC1 Demolition | Labor | 15000 | 0 | 15000 | 11670 | 3330 | 78 | -3330 | 11670
CC2 Framing | Labor | 13000 | 0 | 13000 | 11240 | 1760 | 86 | 2400 | 15400
CC3 Rough-In | Labor | 18500 | 0 | 18500 | 16090 | 2410 | 87 | -2410 | 16090
CC4 Drywall | Labor | 15000 | 0 | 15000 | 13290 | 1710 | 89 | -1710 | 13290
CC5 Fixtures | Labor | 15000 | 3000 | 18000 | 13990 | 4010 | 78 | -4010 | 13990
CC6 Paint | Labor | 8000 | 1600 | 9600 | 12940 | 0 | 135 | 0 | 12940
CC7 Punchlist | Labor | 3000 | 0 | 3000 | 2790 | 210 | 93 | 0 | 3000
CC8 Cleanup | Labor | 0 | 0 | 0 | 2090 | 0 | 0 | 0 | 2090
Materials |  | 35000 | 605.74 | 35605.74 | 26854.05 | 8751.69 | 75 | -1876.9 | 34160.84
CC2 Framing | Materials | 5000 | 0 | 5000 | 5432 | 0 | 109 | 0 | 5432
CC3 Rough-In | Materials | 10000 | 0 | 10000 | 7773.1 | 2226.9 | 78 | -226.9 | 9773.1
CC4 Drywall | Materials | 8000 | 0 | 8000 | 6400 | 1600 | 80 | -1600 | 6400
CC5 Fixtures | Materials | 7500 | 258.7 | 7758.7 | 3846.15 | 3912.55 | 50 | 0 | 7758.7
CC6 Paint | Materials | 3000 | 347.04 | 3347.04 | 2527.8 | 819.24 | 76 | 0 | 3347.04
CC7 Punchlist | Materials | 1000 | 0 | 1000 | 425 | 575 | 43 | 0 | 1000
CC8 Cleanup | Materials | 500 | 0 | 500 | 450 | 50 | 90 | -50 | 450
Equipment |  | 5500 | 0 | 5500 | 4500 | 1000 | 82 | -2500 | 4500
CC3 Rough-In | Equipment | 3000 | 0 | 3000 | 3000 | 0 | 100 | 0 | 3000
CC5 Fixtures | Equipment | 2500 | 0 | 2500 | 0 | 2500 | 0 | -2500 | 0
CC8 Cleanup | Equipment | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500
Subcontractors |  | 3000 | 0 | 3000 | 3000 | 0 | 100 | 0 | 3000
CC8 Cleanup | Subcontractors | 3000 | 0 | 3000 | 3000 | 0 | 100 | 0 | 3000
TOTAL |  | 131000 | 5205.74 | 136205.74 | 118454.05 | 17751.69 | 87 | -13436.9 | 130130.84