## Cost to Complete
Cost to Complete
Through 05/27/2026
Active Projects | 3 | Across 3 Market Areas
Current Budget | $1,001,206 | ▲ $5.2k vs. original
Projected Cost at Completion | $987,106 | Committed + Remaining + Adjustments
Variance | $14,099 | ▲ 1.4% variance
PROJECT | ORIGINAL BUDGET | COR | CURRENT BUDGET | COMMITTED | REMAINING | % USED | ADJUSTMENT | AT COMPLETION
Commercial (C)
2026-3 Office Space Reno | 12000 | 0 | 12000 | 11725.62 | 274.38 | 98 | -350 | 11725.62
Commercial SUBTOTAL | 12000 | 0 | 12000 | 11725.62 | 274.38 | 98 | -350 | 11725.62
Education (E)
2026-2 Elementary Renovation | 853000 | 0 | 853000 | 284250 | 568750 | 33 | -15000 | 841750
Education SUBTOTAL | 853000 | 0 | 853000 | 284250 | 568750 | 33 | -15000 | 841750
Healthcare (H)
26-1 Children's Hospital (Job Costing) | 131000 | 5205.74 | 136205.74 | 121954.05 | 14251.69 | 90 | -13436.9 | 133630.84
Healthcare SUBTOTAL | 131000 | 5205.74 | 136205.74 | 121954.05 | 14251.69 | 90 | -13436.9 | 133630.84
TOTAL | 996000 | 5205.74 | 1001205.74 | 417929.67 | 583276.07 | 42 | -28786.9 | 987106.46